## Backlog_AI_Enhanced
ID | Epic | User Story | Description | Acceptance Criteria | Priority (MoSCoW) | Story Points | Sprint
1 | Auth | Login/Register | As a user, I want to log in/register so that I can access the system | Login works; Register works; Redirect by role | Must | 5 | Sprint 1
2 | TA | Browse Jobs | As a TA, I want to browse jobs so that I can find opportunities | Job list visible; Clickable | Must | 5 | Sprint 1
3 | TA | View Job Details | As a TA, I want details so that I can decide | Full job info shown | Must | 3 | Sprint 1
4 | TA | Apply Job | As a TA, I want to apply so that I can be considered | Submit form; Attach CV | Must | 8 | Sprint 2
5 | TA | Track Status | As a TA, I want to track status | Status visible | Should | 5 | Sprint 2
6 | TA | Manage CV | As a TA, I want to manage CV | Upload/update CV | Must | 3 | Sprint 2
7 | AI | AI Job Recommendation | As a TA, I want AI to recommend jobs so that I can find suitable roles faster | Recommendations shown; Based on profile/CV | Should | 8 | Sprint 2
8 | AI | CV Analysis | As a TA, I want AI to analyse my CV so that I can improve it | Feedback generated; Suggestions provided | Could | 5 | Sprint 2
9 | AI | Application Auto-Fill | As a TA, I want AI to auto-fill forms so that I save time | Fields auto-filled from CV | Should | 5 | Sprint 2
10 | MO | Post Job | As a MO, I want to post jobs | Create & publish job | Must | 8 | Sprint 3
11 | MO | View Applicants | As a MO, I want to view applicants | Applicant list; CV access | Must | 5 | Sprint 3
12 | MO | Filter Applicants | As a MO, I want filtering | Filter/search works | Should | 3 | Sprint 3
13 | MO | Update Status | As a MO, I want to accept/reject | Update status | Must | 5 | Sprint 3
14 | AI | Applicant Ranking | As a MO, I want AI to rank applicants so that I can decide faster | Ranking list generated | Should | 8 | Sprint 3
15 | AI | CV Summarisation | As a MO, I want AI to summarise CVs | Summary displayed | Should | 5 | Sprint 3
16 | Admin | Manage Users | Admin manage users | View/edit users | Should | 5 | Sprint 4
17 | Admin | Search Users | Admin search users | Search works | Should | 3 | Sprint 4
18 | Admin | Filter Users | Admin filter users | Filter works | Should | 3 | Sprint 4
19 | Admin | Manage Jobs | Admin manage jobs | Close/edit jobs | Should | 5 | Sprint 4
20 | Admin | View Applications | Admin view all applications | All visible | Must | 5 | Sprint 4
21 | Admin | Override Status | Admin override decisions | Override works | Must | 5 | Sprint 4
22 | Admin | Workload Management | Admin assign workload | Assign TA; adjust hours | Could | 8 | Sprint 4