## Product Backlog - Group 6
Role | Story ID | Story Name | Epic | Description | Priority | Iteration | Acceptance Criteria | Estimation | Notes | Date started | Date finished
Admin | AD-01 | Admin Login | EP-01 | As an Admin, I want to log in securely, so that I can access management tools. | very high | 1 | • Verify admin credentials via BUPT SSO. • Verify access to admin panel. | 2 | Prerequisite for EP-06. | 2026-03-26 | 2026-03-28
TA | TA-01 | Registration | EP-01 | As a TA, I want to register with @bupt.edu.cn, so that my identity is verified. | very high | 1 | • Verify email validation logic. • Verify successful DB entry for new TA. | 3 | Core security gate. | 2026-03-26 | 2026-03-29
MO | MO-01 | MO Portal | EP-01 | As a MO, I want to access my dashboard, so that I can manage my specific modules. | very high | 1 | • Verify role-based redirection works. • Verify list of assigned modules is visible. | 2 | Primary MO entry point. | 2026-03-28 | 2026-03-31
MO | MO-02 | Create Job | EP-02 | As a MO, I want to create a TA vacancy, so that I can start recruiting. | very high | 1 | • Verify all mandatory fields (hours, GPA). • Verify data persistence in "Draft" mode. | 5 | Foundational for EP-02. | 2026-03-30 | 2026-04-05
TA | TA-02 | Browse Jobs | EP-02 | As a TA, I want to browse all open vacancies, so that I can see opportunities. | very high | 1 | • Verify real-time list of "Open" status jobs. • Verify job details view is clickable. | 3 | Key UX for students. | 2026-04-02 | 2026-04-08
TA | TA-03 | Profile Build | EP-01 | As a TA, I want to upload my CV and set skills, so that I am ready for AI matching. | high | 2 | • Verify PDF upload/preview. • Verify skill tags are saved to profile. | 3 | Essential for EP-04. | 2026-04-09 | 2026-04-12
TA | TA-04 | AI Job Match | EP-04 | As a TA, I want AI to recommend jobs, so that I find roles matching my CV. | high | 2 | • Verify match score (%) display. • Verify "Recommended" tab appears. | 8 | AI Feature (Core) | 2026-04-10 | 2026-04-18
TA | TA-05 | Apply Job | EP-03 | As a TA, I want to submit an application, so that I can be considered for a role. | very high | 2 | • Verify CV is attached to submission. • Verify duplicate application prevention. | 5 | Main transaction Story. | 2026-04-15 | 2026-04-20
TA | TA-06 | AI Auto-fill | EP-04 | As a TA, I want AI to fill the form from my CV, so that the process is faster. | medium | 2 | • Verify data extraction from PDF. • Verify fields (GPA, Name) populate. | 5 | Efficiency enhancement. | 2026-04-17 | 2026-04-22
TA | TA-07 | Track Status | EP-03 | As a TA, I want to track my status, so that I stay informed of the progress. | high | 2 | • Verify status labels: Submitted/S.L./Rejected. | 3 | Dashboard requirement. | 2026-04-19 | 2026-04-22
MO | MO-03 | Review List | EP-03 | As a MO, I want to see all applicants for my job, so that I can screen them. | very high | 3 | • Verify table of all applicants is accessible. • Verify quick link to student CVs. | 5 | Primary MO task. | 2026-04-23 | 2026-04-27
MO | MO-04 | AI Ranker | EP-05 | As a MO, I want AI to rank candidates, so that I identify top talent quickly. | high | 3 | • Verify applicants sorted by AI match degree. • Verify ranking updates with new apps. | 8 | AI Feature (Core) | 2026-04-25 | 2026-05-02
MO | MO-05 | AI CV Summary | EP-05 | As a MO, I want AI to summarize CVs, so that I save time on initial screening. | medium | 3 | • Verify 3-bullet summary on applicant hover. | 5 | Efficiency for faculty. | 2026-04-28 | 2026-05-04
MO | MO-06 | Selection | EP-03 | As a MO, I want to shortlist/reject students, so that I can finalize the team. | very high | 3 | • Verify status update triggers notification. • Verify bulk action for rejection works. | 5 | Selection workflow. | 2026-05-01 | 2026-05-06
MO | MO-07 | AI Interview | EP-05 | As a MO, I want AI to suggest questions, so that I conduct better interviews. | low | 3 | • Verify AI generates 3 tailored questions per CV. | 5 | Advanced AI utility. | 2026-05-04 | 2026-05-06
Admin | AD-02 | User Mgmt | EP-06 | As an Admin, I want to manage user roles, so that I ensure system security. | high | 4 | • Verify Admin can edit or block users. | 5 | Control & Audit. | 2026-05-07 | 2026-05-11
Admin | AD-03 | System Stats | EP-06 | As an Admin, I want to see hiring stats, so that I can monitor the school progress. | medium | 4 | • Verify chart: Applications vs Hirings. | 5 | Governance dashboard. | 2026-05-10 | 2026-05-15
User | SYS-01 | Notifications | EP-06 | As a user, I want email alerts, so that I don't miss status changes. | high | 4 | • Verify SMTP integration for status triggers. | 5 | Communication bridge. | 2026-05-13 | 2026-05-18
User | SYS-02 | Responsive UI | EP-06 | As a user, I want a mobile-friendly site, so that I can apply via phone. | high | 4 | • Verify responsive breakpoints (Mobile/Tab). | 5 | NFR Requirement. | 2026-05-15 | 2026-05-20
User | SYS-03 | Performance | EP-06 | As a user, I want < 2s load time, so that the experience is smooth. | medium | 4 | • Verify page speed on dashboard load. | 3 | NFR Requirement. | 2026-05-18 | 2026-05-20

## Epic Description
Epic ID | Epic Name | Description
EP-01 | Access & Identity | Foundational access control, multi-role login, and comprehensive user profile management for all stakeholders.
EP-02 | Job Lifecycle | Management of the end-to-end job posting process, including creation, publication, editing, and repository maintenance.
EP-03 | Application Flow | Management of the TA application lifecycle, covering resume/CV processing, submission workflows, and status tracking.
EP-04 | AI Student Suite | AI-enhanced tools for applicants, including intelligent job matching, automated CV parsing, and application optimization suggestions.
EP-05 | AI MO Suite | AI-driven screening utilities for Module Organisers, featuring candidate ranking, CV summarization, and interview question generation.
EP-06 | Governance & NFR | System administration, statistical analytics, and fulfillment of Non-Functional Requirements such as performance and mobile responsiveness.